## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
13 | As a player, I want to be able to view the board state so that I can decide what my course of action will be. | 1) Draw Grid Lines | 3 | Clean creation of a grid that reacts to User's mouse hover and mouse click. | User Story | 20 | 20 | Caleb Corlett 100%
|  | 2) Create funcs to move camera (we can decide how user can move camera later, focus on funcs to shift cam position) |  |  |  | 20 | 20 | Caleb Corlett 100%
|  | 3) Define Grid Square Class to hold functions for events |  |  |  | 8 | 8 | Caleb Corlett 100%
|  | 4) On mouse hover, execute func from GSquare obj |  |  |  | 8 | 8 | Caleb Corlett 100%
|  | 5) On mouseUp, execute func from GSquare obj |  |  |  | 8 | 8 | Caleb Corlett 100%
20 | As a player, I want to be able to return to the main menu after a game so that I can navigate easily. | 1) Update Game Stage to Main Menu | 3 | Cleanly transition from another Game Stage back to the Main Menu. | User Story | 1 | x | x
|  | 2) Cleanup midgame objects |  |  |  | 5 | x | x
|  | 3) Setup necessary Main Menu objects (might already exist as a create_main_menu func or something) |  |  |  | 40 | x | x
|  | 4) Display Main Menu UI (might already exist as a create_main_menu func or something) |  |  |  | 20 | x | x
10 | As a player, I want to be able to view the current state of the Haunt Timer at so that I’m able to make tactical decisions about how to play. | 1) Create UI Element To Represent Haunt Timer | 3 | Display an Incrementing Counter element in Midgame Stage UI. | User Story | 3 | x | x
|  | 2) Create func to increment Haunt Timer |  |  |  | 3 | x | x
12 | As a player, I want to be able to have an “inventory” to keep track of my items and what they do. | 1) Create List to store refs to Inventory Items | 3 | Display Inventory Items in Midgame Stage UI and display a larger, more detailed view on mouse hover. | User Story | 1 | x | x
|  | 2) Draw multiple Inventory Items' UI "Small" Elements in the UI |  |  |  | 8 | x | x
|  | 3) On mouse hover, draw Inventory Items' UI "Large" Element |  |  |  | 13 | x | x
29 | As a player, I want to be able to select my own character | 1) Random color selection of character | 3 | Add data for each of the characters and get random color class from the character pool tol assign to the player | User Story | 4 | 4 | Ryan Nodarse 100%
|  | 2) Player chooses between available characters |  |  |  | 4 | x | x
|  | 3) View associated stats etc of characters to the player |  |  |  | 8 | x | x