## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a player, I want to spectate the game after death so that I can see the game’s outcome | 5 | Medium | TODO | 1
2 | As a player, I want to see past effects on my character so that I can understand its current state | 6 | Low | TODO | 55
3 | As a player, I want to see recent actions so that I can understand others’ behavior | 6 | Low | TODO | 34
4 | As a player, I want to see a room’s effects so that I can decide if I want to enter | 5 | High | TODO | 13
5 | As a player, I want to play a tutorial so that I can learn how to play the game. | 6 | Low | TODO | 55
6 | As a player, I want to see my local gameplay stats (games played, times died, etc.) so that I can see, in number form, how my games tend to go | 6 | Low | TODO | 13
7 | As a player, I want to create a custom character (with stats) so that I can create a bit of investment into the world and game | 6 | Low | TODO | 55
8 | As a player, I want a place to view the character lore, so that I can immerse myself more in the world and lore | 6 | Low | TODO | 34
9 | As a player, I want the game elements to evolve as the phase changes so that I feel a difference between the peaceful Exploration Phase and the more chaotic Haunt Phase | 6 | Low | TODO | 34
10 | As a player, I want to be able to view the current state of the Haunt Timer at so that I’m able to make tactical decisions about how to play | 4 | High | DEVELOPING | 8
11 | As a player, I want to be able to change the volume in a settings menu to make the game experience more comfortable with my particular setup | 5 | Medium | TODO | 13
12 | As a player, I want to be able to have an “inventory” to keep track of my items and what they do | 4 | High | DEVELOPING | 21
13 | As a player, I want to be able to view the board state so that I can decide what my course of action will be | 3 | High | COMPLETE | 34
14 | As a player, I want to have a reviewable ruleset to remember my win/loss condition | 5 | High | TODO | 13
15 | As a player I want to be able to keep track of current stat points for users so I can know how many dice to roll and if I will die | 5 | High | TODO | 34
16 | As a player, I want to have the option to change the size of the font in the game | 6 | Low | TODO | 89
17 | As a player, I want to be able to invite friends to my game to play local multiplayer | 6 | Low | TODO | 55
18 | As a player, I want to have a menu for modifiers/house rules before setting up the game | 6 | Low | TODO | 55
19 | As a player, I want to be able to have the ability to pause the game when playing with NPCs | 5 | Medium | TODO | 13
20 | As a player, I want to be able to return to the main menu after a game so that I can navigate easily | 4 | High | COMPLETE | 8
21 | As a player, I want to be able to select my own character | 4 | High | DEVELOPING | 16
22 | As a player, I want to view the order in which players will take their turns in | 5 | Medium | TODO | 16
23 | As a player, I want to play a turn from beginning to end | 5 | High | TODO | 89
24 | As a developer, I want to implement a local database for easier storage of character stats | 4 | High | COMPLETE | 34