## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
13 | Viewable Board | 1) Draw Grid Lines | 2 | Clean creation of a grid that reacts to User's mouse hover and mouse click. | User Story | 20 | 20 | Caleb Corlett 100%
|  | 2) Create funcs to move camera (we can decide how user can move camera later, focus on funcs to shift cam position) |  |  |  | 20 | x | x
|  | 3) Define Grid Square Class to hold functions for events |  |  |  | 8 | 8 | Caleb Corlett 100%
|  | 4) On mouse hover, execute func from GSquare obj |  |  |  | 8 | x | x
|  | 5) On mouseUp, execute func from GSquare obj |  |  |  | 8 | x | x
20 | Return To Main Menu | 1) Update Game Stage to Main Menu | 2 | Cleanly transition from another Game Stage back to the Main Menu | User Story | 1 | x | x
|  | 2) Cleanup midgame objects |  |  |  | 5 | x | x
|  | 3) Setup necessary Main Menu objects (might already exist as a create_main_menu func or something) |  |  |  | 40 | x | x
|  | 4) Display Main Menu UI (might already exist as a create_main_menu func or something) |  |  |  | 20 | x | x