## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
20 | As a player, I want to be able to return to the main menu after a game so that I can navigate easily. | 1) Update Game Stage to Main Menu | 4 | Cleanly transition from another Game Stage back to the Main Menu. | User Story | 1 | 1 | Caleb Corlett 100%
|  | 2) Cleanup midgame objects |  |  |  | 5 | 5 | Caleb Corlett 100%
|  | 3) Setup necessary Main Menu objects (might already exist as a create_main_menu func or something) |  |  |  | 40 | 40 | Caleb Corlett 100%
|  | 4) Display Main Menu UI (might already exist as a create_main_menu func or something) |  |  |  | 20 | 20 | Caleb Corlett 100%
10 | As a player, I want to be able to view the current state of the Haunt Timer at so that I’m able to make tactical decisions about how to play. | 1) Create UI Element To Represent Haunt Timer | 4 | Display an Incrementing Counter element in Midgame Stage UI. | User Story | 3 | x | x
|  | 2) Create func to increment Haunt Timer |  |  |  | 3 | 3 | Patrick Storer 100%
12 | As a player, I want to be able to have an “inventory” to keep track of my items and what they do. | 1) Create Inventory Class | 4 | Display Inventory Items in Midgame Stage UI and display a larger, more detailed view on mouse hover. | User Story | 1 | 1 | Ethan Wyman 100%
|  | 2) Draw multiple Inventory Items' UI "Small" Elements in the UI |  |  |  | 8 | x | x
|  | 3) On mouse hover, draw Inventory Items' UI "Large" Element |  |  |  | 13 | x | x
21 | As a player, I want to be able to select my own character. | 1) Random color selection of character | 4 | Add data for each of the characters and get random color class from the character pool tol assign to the player | User Story | 4 | 4 | Ryan Nodarse 100%
|  | 2) Player chooses between available characters |  |  |  | 4 | 4 | Ryan Nodarse 100%
|  | 3) View associated stats etc of characters to the player |  |  |  | 8 | x | x
24 | As a developer, I want to implement a local database for easier storage of Character stats. | 1) Store Character stats in local SQLite Database upon no existing local DB detected | 4 | Implement and utilize a local Database for storage of Character stats. | User Story | 13 | 13 | Caleb Corlett 100%
|  | 2) Retrieve Character stats stored in local DB |  |  |  | 8 | 8 | Caleb Corlett 100%
|  | 3) Make Character object out of retrieved DB Character data |  |  |  | 8 | 8 | Caleb Corlett 100%