## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
10 | As a player, I want to be able to view the current state of the Haunt Timer at so that I’m able to make tactical decisions about how to play. | 1) Create UI Element To Represent Haunt Timer | 5 | Display an Incrementing Counter element in Midgame Stage UI. | User Story | 3 | x | x
|  | 2) Create func to increment Haunt Timer |  |  |  | 3 | 3 | Patrick Storer 100%
12 | As a player, I want to be able to have an “inventory” to keep track of my items and what they do. | 1) Create Inventory Class | 5 | Display Inventory Items in Midgame Stage UI and display a larger, more detailed view on mouse hover. | User Story | 1 | 1 | Ethan Wyman 100%
|  | 2) Draw multiple Inventory Items' UI "Small" Elements in the UI |  |  |  | 8 | x | x
|  | 3) On mouse hover, draw Inventory Items' UI "Large" Element |  |  |  | 13 | x | x
21 | As a player, I want to be able to select my own character. | 1) Random color selection of character | 5 | Add data for each of the characters and get random color class from the character pool tol assign to the player | User Story | 4 | 4 | Ryan Nodarse 100%
|  | 2) Player chooses between available characters |  |  |  | 4 | 4 | Ryan Nodarse 100%
|  | 3) View associated stats etc of characters to the player |  |  |  | 8 | x | x
25 | As a player I want to place floor tiles around a grid so that I can add to the layout of the mansion. | 1) Implement a few (5) FloorTiles into a FloorTile db | 5 | Randomly draw a FloorTile card from list of valid, available Tile Cards and display them on the FloorGrid. | User Story | 3 | 3 | Caleb Corlett 100%
|  | 2) Create func to randomly draw a floortile id and generate FloorTileLeaf obj with data from DB |  |  |  | 5 | 5 | Caleb Corlett 100%
|  | 3) Create FloorGrid class |  |  |  | 3 | 3 | Caleb Corlett 100%
|  | 4) Create func to place FloorTileLeaf obj into FloorGrid |  |  |  | 5 | 5 | Caleb Corlett 100%
|  | 5) Create func to add FloorTileleaf obj into draw() and make sure they are shown correctly after camera move/zoom |  |  |  | 8 | 8 | Caleb Corlett 100%
|  | 6) Create element in UI to switch the FloorGrid being displayed |  |  |  | 13 | 13 | Caleb Corlett 100%
26 | As a player I want to keep track of events that happen during a turn so that I can view a record of everything that happened in a game. | 1) Display character logos on the FloorGrid | 5 | Create base framework for a game turn with turn events. | User Story | 5 | 5 | Caleb Corlett 100%
|  | 2) Display character card in MidGame UI |  |  |  | 3 | 3 | Caleb Corlett 100%
|  | 3) Create GameTurn class |  |  |  | 13 | 13 | Caleb Corlett 100%
|  | 4) Create TurnQueue |  |  |  | 5 | 5 | Caleb Corlett 100%
|  | 5) Handle end of turn logic + Creation of new turn |  |  |  | 5 | 5 | Caleb Corlett 100%
27 | As a player I want to move a character around the mansion so that I can reach critical objective positions in a game. | 1) Handle additions + rollbacks of movement events (movement phase) | 5 | Implement the different turn_stages. | User Story | 5 | 5 | Caleb Corlett 100%
|  | 2) Handle rotation of FloorTIle after new tile drawn (rotation_phase) |  |  |  | 13 | 13 | Caleb Corlett 100%
|  | 3) End turn after rotation finalized |  |  |  | 1 | 1 | Caleb Corlett 100%
23 | As a player, I want to play a turn from beginning to end | Completed during development of US-27: As a player I want to move a character around the mansion so that I can reach critical objective positions in a game. | 5 | Implement all parts of a turn, from beginning to finish. | User Story | 1 | 1 | Caleb Corlett 100%
22 | As a player, I want to view the order in which players will take their turns in | Completed during development of US-26: As a player I want to keep track of events that happen during a turn so that I can view a record of everything that happened in a game. | 5 | Display visual indicator of turn order for playable characters. | User Story | 1 | 1 | Caleb Corlett 100%
15 | As a player I want to be able to keep track of current stat points for users so I can know how many dice to roll and if I will die | Completed during development of US-26: As a player I want to keep track of events that happen during a turn so that I can view a record of everything that happened in a game. | 5 | Display Character Stat card in MidGame UI. | User Story | 1 | 1 | Caleb Corlett 100%